Reflective diary

Testing phase for the Integrated Care System (ICS) self-assessment and improvement framework for addressing health inequalities through engagement with people and communities.

## This is an anonymised extract from the process reflections of one of the pilot ICSs sites in autumn 2024.

What we did
We (2 x senior engagement, experience and inequalities Integrated Care Board staff and a VCSE leader) established a project group to plan and lead the testing of the ICS Addressing health inequalities through engagement with people and communities self-assessment and improvement framework. The project group met regularly throughout the testing phase.
We identified two system-wide groups to involve in our testing of the self-assessment using the draft version of the framework:
1. Research Engagement Network (REN).
2. Working with People and Communities Advisory Group.
These included a mixture of those working for the ICB, representatives from the VCSE sector, experts by experience and other system partners.
We attended meetings of the two groups and gave them an introduction to the framework. Workshops were then arranged to carry out a self-assessment exercise using the framework. To get started, we chose one project or activity stream for each group to review.
1. The REN ‘Sharing the Power’ project, which aims to build a sustainable and evolving research engagement network reaching people and communities in the county who wanted to be involved in health and care research. The self-assessment focused on the participants’ reflections of the first-year evaluation of REN activity.
2. The People’s Panel project which involves the recruitment of a representative sample of residents (with a particular emphasis in CORE20+ areas) with the purpose of proactively capturing feedback to shape health and care services and support; through regular surveys.

How we did it
To guide the discussion at the self-assessment workshops, we selected a phase of the framework and then translated the criteria under each improvement area within it into a series of relevant conversation prompts.
Our aim was to translate the framework so that we could collaboratively, with a range of stakeholders, identify whether we are emerging, developing, maturing or thriving. For example, the questions that we developed for one of the improvement areas, ‘Planning Evaluation’ under the Evaluate phase, were:
- Was the evaluation planned at the start of the project so the right data could be captured?
- Was the evaluation plan co-produced?
- Were the right skills involved in carrying out the evaluation?

What we learned
- Translating framework sections into specific questions to prompt and guide discussion enabled us to apply it in practice.
- We reflected that in each test group we moved between the levels of practice, going from emerging to maturing for example as the project progressed. We noted that the level of practice may change as projects evolve through the framework’s phases, and the framework can support this progression particularly well if used from the inception of a workstream or project.
- When asking the Advisory Group to assess a project that they were not directly involved in, they did not have the background knowledge required to do this. We think that the framework will be most useful (a) when using it with the project group who are involved in the project and/or (b) with those working at strategic level with the necessary breadth of oversight.
- We discussed whether we should use the framework retrospectively or when planning a project. We used it retrospectively while testing the framework, but in future it would probably be more useful to use from the planning stage and refer to it throughout a project.
- Working through the evaluation phase of the framework generated useful discussions, encouraged helpful and insightful questions, and focussed the discussion around health inequalities.
- The framework feels inclusive. Having funding available for involvement of partners such as VCSEs and lived experience during the testing made it more accessible. Consideration will need to be given to recognition for involvement when the framework is embedded within systems’ working with people and communities processes.
- We liked the assessment words to describe the levels (emerging, developing, maturing, thriving) – they are expansion words and positive. They emphasise that this is a dynamic process and there is always room for improvement.
- Working through the framework forced us to be transparent about our processes and admit where things could have been done better, which is important for building trust.